## SPASS_S46-Port1_080605
Request | Riders | Start (SCET) | Start (Epoch) | Duration | End (SCET) | Primary | Secondary | Comments
Sequence S46, length = 44 days |  | 2008-331T17:55:00 |  | 043T21:21:00 | 2009-009T15:16:00
RINGS_94B Segment |  | 2008-331T17:55:00 |  | 001T06:15:00 | 2008-333T00:10:00
SP_094EA_S46IVP331_PRIME |  | 2008-331T17:55:00 |  | 000T00:06:00 | 2008-331T18:01:00 | XBAND to Earth | NEG_X to NEP | S46 IVP Gap
NAV_094SK_OPNAV311_PRIME |  | 2008-331T18:01:00 |  | 000T01:28:00 | 2008-331T19:29:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Earth point, end at New Waypoint
NAV_094SA_WAYPTTURN311_PRIME |  | 2008-331T19:29:00 |  | 000T00:01:00 | 2008-331T19:30:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-331T19:30:00 |  | 001T05:20:00 | 2008-333T00:50:00 | ISS_NAC to Saturn | NEG_X to Sun
NAV_094SK_SFAD001_PRIME |  | 2008-331T19:30:00 |  | 000T02:00:00 | 2008-331T21:30:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at waypoint point, end at Waypoint
ISS_094RI_RADMRLPLF001_PRIME | U, V | 2008-331T21:30:00 |  | 000T04:05:00 | 2008-332T01:35:00 | ISS_NAC to Rings | PIC
CIRS_094SA_COMPSIT002_PRIME |  | 2008-332T01:35:00 |  | 000T08:30:00 | 2008-332T10:05:00 | CIRS_FP1 to Saturn | POS_Z to NSP
CAPS_094SA_SURVEYPTG005_PRIME |  | 2008-332T10:05:00 |  | 000T02:00:00 | 2008-332T12:05:00 | POS_Y to COROT | NEG_X to Sun
ISS_094OT_SATELLORB010_PRIME |  | 2008-332T12:05:00 |  | 000T00:30:00 | 2008-332T12:35:00 | ISS_NAC to Rocks | NEG_X to Sun
UVIS_094ST_URTHEHYA001_PRIME | U | 2008-332T12:35:00 |  | 000T01:55:00 | 2008-332T14:30:00 | UVIS_FUV to 138.591/2.314 | POS_Z to NSP
SP_094EA_DLTURN332_PRIME |  | 2008-332T14:30:00 |  | 000T00:40:00 | 2008-332T15:10:00 | XBAND to Earth | NEG_X to 269.8/54.5
SP_094EA_C34HEFOTP332_PRIME | C, N | 2008-332T15:10:00 |  | 000T09:00:00 | 2008-333T00:10:00 | XBAND to Earth | 4_Hr_Rolling | NEG_X to 269.8/54.5 for CDA
SATURN_94_95 Segment |  | 2008-333T00:10:00 |  | 006T17:16:00 | 2008-339T17:26:00
SP_094SA_WAYPTTURN333_PRIME |  | 2008-333T00:10:00 |  | 000T00:40:00 | 2008-333T00:50:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-333T00:50:00 |  | 000T17:46:00 | 2008-333T18:36:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_094TI_MR3CLD333_PRIME | C | 2008-333T00:50:00 | E094_MR3CLD333+000T00:00:00 | 000T01:15:00 | 2008-333T02:05:00 | ISS_NAC to Titan | NEG_X to Sun
ISS_094OT_SATELLORB014_PRIME |  | 2008-333T02:05:00 |  | 000T00:30:00 | 2008-333T02:35:00 | ISS_NAC to Rocks | NEG_X to Sun
UVIS_094SA_EUVFUV001_PRIME | C | 2008-333T02:35:00 |  | 000T05:41:00 | 2008-333T08:16:00 | UVIS_FUV to Saturn (-1.148,0.0,2.977 deg. offset) | POS_Z to NSP
SP_094EA_DLTURN333_PRIME |  | 2008-333T08:16:00 |  | 000T00:40:00 | 2008-333T08:56:00 | XBAND to Earth | NEG_X to 269.8/54.5
SP_094EA_G34BWGOTB333_PRIME | C, N | 2008-333T08:56:00 |  | 000T09:00:00 | 2008-333T17:56:00 | XBAND to Earth | 6_Hr_Rolling | NEG_X to 269.8/54.5
Apoapse Per = 8.0 d, inc =... |  | 2008-333T09:29:06 |  | 000T00:00:01 | 2008-333T09:29:07
SP_095SA_WAYPTTURN433_PRIME |  | 2008-333T17:56:00 |  | 000T00:25:00 | 2008-333T18:21:00 | ISS_NAC to Saturn (0.0,-40.0,0.0 deg. offset) | NEG_Z to Sun | Part 1 of 2-Part Turn
SP_095SA_WAYPTTURN533_PRIME |  | 2008-333T18:21:00 |  | 000T00:15:00 | 2008-333T18:36:00 | ISS_NAC to Saturn | NEG_Z to Sun | Part 2 of 2-Part Turn
NEW WAYPOINT |  | 2008-333T18:36:00 |  | 000T23:45:00 | 2008-334T18:21:00 | ISS_NAC to Saturn | NEG_Z to Sun
CIRS_095SA_FIRMAP001_PRIME |  | 2008-333T18:36:00 |  | 000T12:55:00 | 2008-334T07:31:00 | CIRS_FP1 to Saturn | POS_X to NSP
ISS_095OT_SATELLORB001_PRIME |  | 2008-334T07:31:00 |  | 000T00:30:00 | 2008-334T08:01:00 | ISS_NAC to Rocks | NEG_Z to Sun
SP_095EA_DLTURN334_PRIME |  | 2008-334T08:01:00 |  | 000T00:20:00 | 2008-334T08:21:00 | XBAND to Earth (0.0,0.0,-80.0 deg. offset) | POS_X to NEP | Part 1 of 2-Part Turn
SP_095EA_DLTURN434_PRIME |  | 2008-334T08:21:00 |  | 000T00:20:00 | 2008-334T08:41:00 | XBAND to Earth | POS_X to NEP | Part 2 of 2-Part Turn
SP_095EA_G34BWGNON334_PRIME | C | 2008-334T08:41:00 |  | 000T09:00:00 | 2008-334T17:41:00 | XBAND to Earth | 6_Hr_Rolling | POS_X to NEP; 6 hr roll, 3 hr dscal
SP_095SA_WAYPTTURN334_PRIME |  | 2008-334T17:41:00 |  | 000T00:40:00 | 2008-334T18:21:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-334T18:21:00 |  | 004T23:45:00 | 2008-339T18:06:00 | ISS_NAC to Saturn | NEG_X to Sun
CAPS_095SA_SURVEYPTG001_PRIME |  | 2008-334T18:21:00 |  | 000T02:00:00 | 2008-334T20:21:00 | POS_Z to Saturn | NEG_X to Sun
UVIS_095SA_NPOLEAUR001_PRIME | I, V | 2008-334T20:21:00 |  | 000T11:40:00 | 2008-335T08:01:00 | ISS_NAC to Saturn | NEG_X to Sun
SP_095EA_DLTURN335_PRIME |  | 2008-335T08:01:00 |  | 000T00:40:00 | 2008-335T08:41:00 | XBAND to Earth | POS_X to NSP
SP_095EA_G70METNON335_PRIME | C | 2008-335T08:41:00 |  | 000T09:00:00 | 2008-335T17:41:00 | XBAND to Earth | Rolling/Bias | POS_X to NEP
NAV_095SK_OPNAV351_PRIME |  | 2008-335T17:41:00 |  | 000T01:29:00 | 2008-335T19:10:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at earth point, end at waypoint
NAV_095SK_WAYPTTURN351_PRIME |  | 2008-335T19:10:00 |  | 000T00:01:00 | 2008-335T19:11:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_095SA_NPOLEDYN001_PRIME | I, R, U | 2008-335T19:11:00 |  | 000T13:05:00 | 2008-336T08:16:00 | ISS_NAC to Saturn | NEG_X to NSP
RADAR_095SA_NORTHPOL001_PRIME |  | 2008-336T08:16:00 |  | 000T06:00:00 | 2008-336T14:16:00 | NEG_Z to Saturn | PIC
SP_095EA_DLTURN336_PRIME |  | 2008-336T14:16:00 |  | 000T00:40:00 | 2008-336T14:56:00 | XBAND to Earth | POS_X to 270.0/55.0 | Secondary for MIMI
SP_095EA_C34BWGOTP336_PRIME | C, M, N | 2008-336T14:56:00 |  | 000T09:00:00 | 2008-336T23:56:00 | XBAND to Earth | 4_Hr_Rolling
SP_095SA_WAYPTTURN336_PRIME | M | 2008-336T23:56:00 |  | 000T00:40:00 | 2008-337T00:36:00 | ISS_NAC to Saturn | NEG_X to Sun
CAPS_095SA_AURXNGPTG001_PRIME | M | 2008-337T00:36:00 |  | 000T03:24:00 | 2008-337T04:00:00 | POS_X to B_Field (0.0,0.0,10.0 deg. offset) | NEG_Y to Saturn
ISS_095EN_GEOLOG001_PRIME | C, M, U, V | 2008-337T04:00:00 |  | 000T02:30:00 | 2008-337T06:30:00 | ISS_NAC to Enceladus | NEG_X to Sun | NAC to Enceladus
CDA_095DR_RPX0140002_PRIME | M, V | 2008-337T06:30:00 |  | 000T03:00:00 | 2008-337T09:30:00 | NEG_X to Sun | NEG_Z to Saturn
Periapse R = 5.213 Rs, lat ... |  | 2008-337T09:06:50 |  | 000T00:00:01 | 2008-337T09:06:51
ISS_095SA_AURMOV001_PRIME | M, U | 2008-337T09:30:00 |  | 000T04:46:00 | 2008-337T14:16:00 | ISS_WAC to Saturn | NEG_Z to NSP
SP_095EA_DLTURN337_PRIME | M | 2008-337T14:16:00 |  | 000T00:40:00 | 2008-337T14:56:00 | XBAND to Earth | NEG_X to NEP
SP_095EA_G70METOTB337_PRIME | C, M, N | 2008-337T14:56:00 |  | 000T03:00:00 | 2008-337T17:56:00 | XBAND to Earth | NEG_X to NEP | OTMBU bias; no split roll
SP_095EA_C34BWGOTB437_PRIME | C, E, M, N | 2008-337T17:56:00 |  | 000T06:00:00 | 2008-337T23:56:00 | XBAND to Earth | NEG_X to NEP
SP_095SA_WAYPTTURN337_PRIME | R | 2008-337T23:56:00 |  | 000T00:40:00 | 2008-338T00:36:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_095SA_SPOLEDYN001_PRIME | I, R, U | 2008-338T00:36:00 |  | 000T02:20:00 | 2008-338T02:56:00 | ISS_NAC to Saturn | NEG_X to NSP
RADAR_095SA_SOUTHPOL001_PRIME |  | 2008-338T02:56:00 |  | 000T04:50:00 | 2008-338T07:46:00 | NEG_Z to Saturn | PIC
SP_095EA_DLTURN338_PRIME |  | 2008-338T07:46:00 |  | 000T00:40:00 | 2008-338T08:26:00 | XBAND to Earth | NEG_X to NEP
SP_095EA_G70METNON338_PRIME | C | 2008-338T08:26:00 |  | 000T09:00:00 | 2008-338T17:26:00 | XBAND to Earth | Rolling/Bias | NEG_X to NEP
SP_095SA_WAYPTTURN338_PRIME |  | 2008-338T17:26:00 |  | 000T00:40:00 | 2008-338T18:06:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_095SA_SPOLEDYN002_PRIME | C, I, U | 2008-338T18:06:00 |  | 000T08:40:00 | 2008-339T02:46:00 | ISS_NAC to Saturn | NEG_X to NSP
ISS_095TI_MR1CLDF338_PRIME | C | 2008-339T02:46:00 | E095_MR1CLDF338+000T00:00:00 | 000T01:15:00 | 2008-339T04:01:00 | ISS_NAC to Titan | NEG_Z to Sun
MAG_095SU_CALROLL001_PRIME |  | 2008-339T04:01:00 |  | 000T06:45:00 | 2008-339T10:46:00 | NEG_X to Sun (0.0,0.0,-30.0 deg. offset) | Rolling
SP_095EA_DLTURN339_PRIME |  | 2008-339T10:46:00 |  | 000T00:40:00 | 2008-339T11:26:00 | XBAND to Earth | NEG_X to NEP
SP_095EA_G70METNON339_PRIME | C | 2008-339T11:26:00 |  | 000T03:00:00 | 2008-339T14:26:00 | XBAND to Earth | NEG_X to NEP
SP_095EA_G34BWGNON339_PRIME | C | 2008-339T14:26:00 |  | 000T03:00:00 | 2008-339T17:26:00 | XBAND to Earth | NEG_X to NEP | no rolling, CIRS pre-TOST
Titan Flyby T48 Segment |  | 2008-339T17:26:00 |  | 002T04:01:00 | 2008-341T21:27:00
SP_095TI_WAYPTTURN339_PRIME |  | 2008-339T17:26:00 |  | 000T00:40:00 | 2008-339T18:06:00 | NEG_Y to Titan | NEG_X to 30.0/50.0
NEW WAYPOINT |  | 2008-339T18:06:00 |  | 002T04:01:00 | 2008-341T22:07:00 | NEG_Y to Titan | NEG_X to 30.0/50.0
SP_095TI_DEADTIME339_PRIME |  | 2008-339T18:06:00 |  | 000T00:15:33 | 2008-339T18:21:33 | NEG_Y to Titan | NEG_X to 30.0/50.0
VIMS_095TI_GLOBMAP001_PRIME | C, I | 2008-339T18:21:33 | GMB_E095_Titan48-000T20:04:12 | 000T07:04:12 | 2008-340T01:25:45 | VIMS_IR to Titan | NEG_X to Sun
CIRS_095TI_FIRNADCMP001_PRIME | C, I, R, U, V | 2008-340T01:25:45 | GMB_E095_Titan48-000T13:00:00 | 000T04:00:00 | 2008-340T05:25:45 | CIRS_FP1 to Titan | PIC
ISS_095TI_GLOBMAP001_PRIME | C, R, V | 2008-340T05:25:45 | GMB_E095_Titan48-000T09:00:00 | 000T04:00:00 | 2008-340T09:25:45 | ISS_NAC to Titan | NEG_X to Sun
ISS_095TI_REGMAP001_PRIME | C, R, V | 2008-340T09:25:45 | GMB_E095_Titan48-000T05:00:00 | 000T02:00:00 | 2008-340T11:25:45 | ISS_NAC to Titan | NEG_X to Sun
CIRS_095TI_FIRLMBINT001_PRIME | C, I, M, R, U, V | 2008-340T11:25:45 | GMB_E095_Titan48-000T03:00:00 | 000T01:00:00 | 2008-340T12:25:45 | CIRS_FP1 to Titan | PIC
ISS_095TI_HIGHRES001_PRIME | C, M, R, V | 2008-340T12:25:45 | GMB_E095_Titan48-000T02:00:00 | 000T00:48:00 | 2008-340T13:13:45 | ISS_NAC to Titan | NEG_X to Sun
ENGR_095SC_RADRCS340_PRIME | C, M, R | 2008-340T13:13:45 | GMB_E095_Titan48-000T01:12:00 | 000T00:01:00 | 2008-340T13:14:45 | NEG_Y to Titan (0.0,-40.0,0.0 deg. offset) | NEG_X to Sun | DB (.5,.5,.5)
ISS_095TI_TRNSITION001_PRIME | C, M, R | 2008-340T13:14:45 | GMB_E095_Titan48-000T01:11:00 | 000T00:21:00 | 2008-340T13:35:45 | ISS_NAC to Titan | NEG_X to Sun
Begin Custom Period |  | 2008-340T13:35:45 | GMB_E095_Titan48-000T00:50:00 | 000T00:00:01 | 2008-340T13:35:46
RADAR_095TI_T48IHISAR001_PRIME | M | 2008-340T13:35:45 | GMB_E095_Titan48-000T00:50:00 | 000T00:20:00 | 2008-340T13:55:45 | NEG_Z to Titan | NEG_X to 30.0/50.0 | Pick up at NEG_Y to Titan, NEG_X to 30.0/50.0; Hand off at NEG_Z to Titan, NEG_X to 30.0/50.0.
RADAR_095TI_T48INALT001_PRIME | M | 2008-340T13:55:45 | GMB_E095_Titan48-000T00:30:00 | 000T00:12:00 | 2008-340T14:07:45 | NEG_Z to Titan | NEG_X to SC_RAM | Pick up at NEG_Z to Titan, NEG_X to 30.0/50.0; Hand off at NEG_Z to Titan, NEG_X to SC_RAM.
Begin Dual Playback Science |  | 2008-340T14:07:45 | GMB_E095_Titan48-000T00:18:00 | 000T00:00:01 | 2008-340T14:07:46
RADAR_095TI_T48INSAR001_PRIME | M | 2008-340T14:07:45 | GMB_E095_Titan48-000T00:18:00 | 000T00:13:00 | 2008-340T14:20:45 | NEG_Z to Titan | NEG_X to Titan_SC_RAM | Pick up at NEG_Z to Titan, NEG_X to SC_RAM; Hand off at NEG_X to SC_RAM, NEG_Z to Titan. Must be at INMS attitude by -0:05:00.
RADAR_095TI_T48RASAR001_PRIME | C, M, V | 2008-340T14:20:45 | GMB_E095_Titan48-000T00:05:00 | 000T00:27:00 | 2008-340T14:47:45 | NEG_X to Titan_SC_RAM | NEG_Z to Titan | Pick up at NEG_X to SC_RAM, NEG_Z to Titan; Hand off at UVIS_FUV to 104.656/-28.972, NEG_X to 37.0/55.0. Ride-along.
95TI (t) T48 TITAN Outbou... |  | 2008-340T14:25:45 |  | 000T00:00:01 | 2008-340T14:25:46
End Dual Playback Science |  | 2008-340T14:40:45 | GMB_E095_Titan48+000T00:15:00 | 000T00:00:01 | 2008-340T14:40:46
ENGR_095SC_DFPWBIAS340_PPS | C, M, V | 2008-340T14:47:40 | GMB_E095_Titan48+000T00:21:55 | 000T00:21:09 | 2008-340T15:08:49 | UVIS_FUV to 104.656/-28.972 (0.258,0.0,0.0 deg. offset) | NEG_X to Sun | Pick up at UVIS_FUV to 104.656/-28.972 (0.258,0.0,0.0 deg. offset), NEG_X to Sun; Hand off at UVIS_FUV to 104.656/-28.972 (0.258,0.0,0.0 deg. offset), NEG_X to Sun. Deadband = (.5,.5,.5)
UVIS_095ST_EPSCMATI001_PRIME | C, M, V | 2008-340T14:47:45 | GMB_E095_Titan48+000T00:22:00 | 000T00:33:00 | 2008-340T15:20:45 | UVIS_FUV to 104.656/-28.972 (0.258,0.0,0.0 deg. offset) | NEG_X to Sun | Pick up at UVIS_FUV to 104.656/-28.972, NEG_X to 37.0/55.0; Hand off at unknown, unknown.
End Custom Period |  | 2008-340T15:20:45 | GMB_E095_Titan48+000T00:55:00 | 000T00:00:01 | 2008-340T15:20:46
CIRS_095TI_FIRLMBINT002_PRIME | C, I, M, U, V | 2008-340T15:20:45 | GMB_E095_Titan48+000T00:55:00 | 000T01:20:00 | 2008-340T16:40:45 | CIRS_FP1 to Titan | PIC
UVIS_095TI_EUVFUV001_PRIME | C, I, V | 2008-340T16:40:45 | GMB_E095_Titan48+000T02:15:00 | 000T06:45:00 | 2008-340T23:25:45 | UVIS_FUV to Titan | NEG_X to Sun
Apoapse Per = 8.0 d, inc =... |  | 2008-340T18:19:47 |  | 000T00:00:01 | 2008-340T18:19:48
VIMS_096TI_CLOUDMAP001_PRIME | C, I | 2008-340T23:25:45 | GMB_E095_Titan48+000T09:00:00 | 000T04:00:00 | 2008-341T03:25:45 | VIMS_IR to Titan | NEG_X to Sun
ISS_096TI_NIGHTNAC001_PRIME | C, V | 2008-341T03:25:45 | GMB_E095_Titan48+000T13:00:00 | 000T01:00:00 | 2008-341T04:25:45 | ISS_NAC to Titan | NEG_X to Sun
CIRS_096TI_MIDIRTMAP001_PRIME | C, I, V | 2008-341T04:25:45 | GMB_E095_Titan48+000T14:00:00 | 000T03:06:48 | 2008-341T07:32:33 | CIRS_FPB to Titan | POS_X to North_Pole_Dir
SP_096TI_DEADTIME341_PRIME |  | 2008-341T07:32:33 | GMB_E095_Titan48+000T17:06:48 | 000T00:14:27 | 2008-341T07:47:00 | NEG_Y to Titan | NEG_X to 30.0/50.0
SP_096EA_DLTURN341_PRIME |  | 2008-341T07:47:00 |  | 000T00:40:00 | 2008-341T08:27:00 | XBAND to Earth | POS_X to NEP
SP_096EA_G70METNON341_PRIME | C | 2008-341T08:27:00 |  | 000T09:00:00 | 2008-341T17:27:00 | XBAND to Earth | Rolling/Bias | POS_X to NEP
Pointer Reset in preparatio... |  | 2008-341T17:27:00 |  | 000T00:00:01 | 2008-341T17:27:01
SP_096EA_C70METNON341_PRIME | C | 2008-341T17:27:00 |  | 000T04:00:00 | 2008-341T21:27:00 | XBAND to Earth | NEG_X to NEP | DSCAL over dual playback
RINGS_96_97 Segment |  | 2008-341T21:27:00 |  | 007T01:46:00 | 2008-348T23:13:00
SP_096SA_WAYPTTURN341_PRIME |  | 2008-341T21:27:00 |  | 000T00:40:00 | 2008-341T22:07:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-341T22:07:00 |  | 007T01:46:00 | 2008-348T23:53:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_096RI_TMAPN20LP001_PRIME | C, I, U | 2008-341T22:07:00 |  | 000T06:55:00 | 2008-342T05:02:00 | CIRS_FP1 to Rings | NEG_X to Sun
CAPS_096SA_SURVEYPTG002_PRIME |  | 2008-342T05:02:00 |  | 000T02:00:00 | 2008-342T07:02:00 | POS_Z to Saturn (0.0,0.0,12.0 deg. offset) | POS_X to NSP
ISS_096OT_SATELLORB005_PRIME |  | 2008-342T07:02:00 |  | 000T00:30:00 | 2008-342T07:32:00 | ISS_NAC to Rocks | NEG_X to Sun
SP_096EA_DLTURN342_PRIME |  | 2008-342T07:32:00 |  | 000T00:40:00 | 2008-342T08:12:00 | XBAND to Earth | NEG_X to NEP
SP_096EA_G34BWGNON342_PRIME | C | 2008-342T08:12:00 |  | 000T09:00:00 | 2008-342T17:12:00 | XBAND to Earth | 4_Hr_Rolling | NEG_X to NEP; 4 hr roll, 3 hr dscal
SP_096SA_WAYPTTURN342_PRIME |  | 2008-342T17:12:00 |  | 000T00:40:00 | 2008-342T17:52:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_096RI_TMAPN45LP001_PRIME | C, U, V | 2008-342T17:52:00 |  | 000T05:20:00 | 2008-342T23:12:00 | CIRS_FP1 to Rings | NEG_X to Sun
NAV_096SK_OPNAV421_PRIME | C | 2008-342T23:12:00 |  | 000T01:29:00 | 2008-343T00:41:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_096EA_DLTURN421_PRIME |  | 2008-343T00:41:00 |  | 000T00:01:00 | 2008-343T00:42:00 | XBAND to Earth | POS_X to NEP
SP_096EA_M34HEFNON343_PRIME | C | 2008-343T00:42:00 |  | 000T09:00:00 | 2008-343T09:42:00 | XBAND to Earth | Rolling/SRU | POS_X to NEP
SP_096SA_WAYPTTURN343_PRIME |  | 2008-343T09:42:00 |  | 000T00:26:00 | 2008-343T10:08:00 | ISS_NAC to Saturn | NEG_X to Sun | 24 min
VIMS_096RI_GAMCRUOCC011_PRIME | U | 2008-343T10:08:00 |  | 000T04:28:00 | 2008-343T14:36:00 | VIMS_IR to 187.791/-57.113 | NEG_X to Sun
ISS_096RI_RETARMRMP001_PRIME | C | 2008-343T14:36:00 |  | 000T01:33:00 | 2008-343T16:09:00 | ISS_NAC to Rings | PIC
UVIS_096ST_URBETCEN001_PRIME | I, U | 2008-343T16:09:00 |  | 000T05:00:00 | 2008-343T21:09:00 | UVIS_FUV to 210.956/-60.373 | POS_X to L_ANSA_A
ISS_096RF_FRINGHRDF001_PRIME | C | 2008-343T21:09:00 |  | 000T07:22:00 | 2008-344T04:31:00 | ISS_NAC to Rings | PIC
UVIS_096ST_URALPARA001_PRIME | M | 2008-344T04:31:00 |  | 000T06:08:00 | 2008-344T10:39:00 | UVIS_FUV to 262.96/-49.876 | POS_X to L_ANSA_A
VIMS_096RI_SPOKE105_PRIME | C, I, M, U | 2008-344T10:39:00 |  | 000T01:22:00 | 2008-344T12:01:00 | VIMS_IR to Rings | POS_Z to NSP
CIRS_096TE_FP1SECLN001_PRIME | C, I, M, U, V | 2008-344T12:01:00 |  | 000T01:54:00 | 2008-344T13:55:00 | CIRS_FP3 to Tethys | NEG_X to Sun
SP_096EA_DLTURN344_PRIME | M | 2008-344T13:55:00 |  | 000T00:32:00 | 2008-344T14:27:00 | XBAND to Earth | NEG_X to 261.2/-16.1 | 30 min
SP_096EA_C70METOTP344_PRIME | C, M, N | 2008-344T14:27:00 |  | 000T09:00:00 | 2008-344T23:27:00 | XBAND to Earth | NEG_X to 261.2/-16.1 | Secondary for CDA vertical ring plane crossing.
Periapse R = 5.765 Rs, lat ... |  | 2008-344T18:07:23 |  | 000T00:00:01 | 2008-344T18:07:24
SP_096SA_WAYPTTURN344_PRIME | M | 2008-344T23:27:00 |  | 000T00:25:00 | 2008-344T23:52:00 | ISS_NAC to Saturn | NEG_X to Sun | 21 min
VIMS_096RI_HIRESHIPH101_PRIME | C, M, U | 2008-344T23:52:00 |  | 000T01:15:00 | 2008-345T01:07:00 | VIMS_IR to Rings | NEG_X to Sun
ISS_096RI_AZSCANLIT001_PRIME | C, M | 2008-345T01:07:00 |  | 000T06:35:00 | 2008-345T07:42:00 | ISS_NAC to Rings | PIC
SP_096EA_DLTURN345_PRIME |  | 2008-345T07:42:00 |  | 000T00:30:00 | 2008-345T08:12:00 | XBAND to Earth | NEG_X to 261.2/-16.1 | 20 min
SP_096EA_G70METOTB345_PRIME | C, N | 2008-345T08:12:00 |  | 000T09:00:00 | 2008-345T17:12:00 | XBAND to Earth | 5_Hr_Rolling | NEG_X to NEP
SP_096SA_WAYPTTURN345_PRIME |  | 2008-345T17:12:00 |  | 000T00:40:00 | 2008-345T17:52:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_096RF_FMOVIE004_PRIME | C, V | 2008-345T17:52:00 |  | 000T12:55:00 | 2008-346T06:47:00 | ISS_NAC to Rings | PIC
ISS_096OT_SATELLORB008_PRIME |  | 2008-346T06:47:00 |  | 000T00:30:00 | 2008-346T07:17:00 | ISS_NAC to Rocks | NEG_X to Sun
SP_096EA_DLTURN346_PRIME |  | 2008-346T07:17:00 |  | 000T00:40:00 | 2008-346T07:57:00 | XBAND to Earth | NEG_X to NEP
SP_096EA_G34BWGNON346_PRIME | C | 2008-346T07:57:00 |  | 000T09:00:00 | 2008-346T16:57:00 | XBAND to Earth | 5_Hr_Rolling | NEG_X to NEP; 6 hr roll, 3 hr dscal
SP_096SA_WAYPTTURN346_PRIME |  | 2008-346T16:57:00 |  | 000T00:40:00 | 2008-346T17:37:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_096RI_SPKFMLFLP001_PRIME | V | 2008-346T17:37:00 |  | 000T05:10:00 | 2008-346T22:47:00 | ISS_NAC to Rings | PIC
ISS_096OT_SATELLORB009_PRIME |  | 2008-346T22:47:00 |  | 000T00:30:00 | 2008-346T23:17:00 | ISS_NAC to Rocks | NEG_X to Sun
VIMS_096RI_APOMOSL114_PRIME | C, U | 2008-346T23:17:00 |  | 000T08:00:00 | 2008-347T07:17:00 | VIMS_IR to Rings | POS_Z to NSP
SP_096EA_DLTURN347_PRIME |  | 2008-347T07:17:00 |  | 000T00:40:00 | 2008-347T07:57:00 | XBAND to Earth | NEG_X to NEP
SP_096EA_G70METNON347_PRIME | C | 2008-347T07:57:00 |  | 000T09:00:00 | 2008-347T16:57:00 | XBAND to Earth | Rolling/Bias | NEG_X to NEP
SP_096SA_WAYPTTURN347_PRIME |  | 2008-347T16:57:00 |  | 000T00:40:00 | 2008-347T17:37:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_096TI_MR3CLD347_PRIME | U | 2008-347T17:37:00 | E096_MR3CLD347+000T00:00:00 | 000T01:15:00 | 2008-347T18:52:00 | ISS_NAC to Titan | NEG_X to Sun
CIRS_096RI_SUBMS10LP001_PRIME | C, I, U, V | 2008-347T18:52:00 |  | 000T08:00:00 | 2008-348T02:52:00 | CIRS_FP1 to Rings | NEG_X to Sun
ISS_096OT_SATELLORB013_PRIME |  | 2008-348T02:52:00 |  | 000T00:30:00 | 2008-348T03:22:00 | ISS_NAC to Rocks | NEG_X to Sun
CAPS_096SA_SURVEYPTG004_PRIME | C | 2008-348T03:22:00 |  | 000T02:00:00 | 2008-348T05:22:00 | POS_Z to Saturn (0.0,-20.0,10.0 deg. offset) | POS_X to NSP
ISS_096RI_FMONITOR002_PRIME | C, V | 2008-348T05:22:00 |  | 000T03:00:00 | 2008-348T08:22:00 | ISS_NAC to Rings | NEG_X to Sun
ISS_096OT_SATELLORB014_PRIME |  | 2008-348T08:22:00 |  | 000T00:30:00 | 2008-348T08:52:00 | ISS_NAC to Rocks | NEG_X to Sun
UVIS_096EN_ICYATM001_PRIME | I | 2008-348T08:52:00 |  | 000T04:06:00 | 2008-348T12:58:00 | UVIS_FUV to Enceladus (0.0,0.0,-0.115 deg. offset) | POS_Z to NSP | See observation description. Duration of 4 hours allows for 30 min slew to and from Enceladus, and 3 integration sites.
NAV_096SK_OPNAV481_PRIME | N | 2008-348T12:58:00 |  | 000T01:14:00 | 2008-348T14:12:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_096EA_DLTURN481_PRIME |  | 2008-348T14:12:00 |  | 000T00:01:00 | 2008-348T14:13:00 | XBAND to Earth | NEG_X to 271.4/58.4
SP_096EA_C34HEFOTP348_PRIME | C, N | 2008-348T14:13:00 |  | 000T09:00:00 | 2008-348T23:13:00 | XBAND to Earth | 4_Hr_Rolling | NEG_X to 271.4/58.4 for CDA
Apoapse Per = 8.0 d, inc =... |  | 2008-348T17:46:19 |  | 000T00:00:01 | 2008-348T17:46:20
SATURN_97 Segment |  | 2008-348T23:13:00 |  | 006T17:16:00 | 2008-355T16:29:00
SP_097SA_WAYPTTURN348_PRIME |  | 2008-348T23:13:00 |  | 000T00:40:00 | 2008-348T23:53:00 | ISS_NAC to Saturn | POS_Z to NSP | SP Turn to Waypoint
NEW WAYPOINT |  | 2008-348T23:53:00 |  | 002T09:35:00 | 2008-351T09:28:00 | ISS_NAC to Saturn | POS_Z to NSP
CIRS_097SA_COMPSIT001_PRIME | V | 2008-348T23:53:00 |  | 000T07:25:00 | 2008-349T07:18:00 | CIRS_FP1 to Saturn | POS_Z to NSP
SP_097EA_DLTURN349_PRIME |  | 2008-349T07:18:00 |  | 000T00:40:00 | 2008-349T07:58:00 | XBAND to Earth | NEG_X to 271.4/58.4
SP_097EA_G34BWGOTB349_PRIME | C, N | 2008-349T07:58:00 |  | 000T09:00:00 | 2008-349T16:58:00 | XBAND to Earth | 6_Hr_Rolling | NEG_X to 271.4/58.4 for CDA
SP_097SA_WAYPTTURN349_PRIME |  | 2008-349T16:58:00 |  | 000T00:40:00 | 2008-349T17:38:00 | ISS_NAC to Saturn | POS_Z to NSP | SP Turn to Waypoint
ISS_097OT_SATELLORB003_PRIME |  | 2008-349T17:38:00 |  | 000T00:50:00 | 2008-349T18:28:00 | ISS_NAC to Rocks | POS_Z to NSP
CIRS_097SA_COMPSIT002_PRIME | V | 2008-349T18:28:00 |  | 000T12:35:00 | 2008-350T07:03:00 | CIRS_FP1 to Saturn | POS_Z to NSP
SP_097EA_DLTURN350_PRIME |  | 2008-350T07:03:00 |  | 000T00:40:00 | 2008-350T07:43:00 | XBAND to Earth | POS_X to NEP
SP_097EA_G34BWGNON350_PRIME | C | 2008-350T07:43:00 |  | 000T09:00:00 | 2008-350T16:43:00 | XBAND to Earth | 6_Hr_Rolling | POS_X to NEP; 6 hr roll, 3 hr dscal
SP_097SA_WAYPTTURN350_PRIME |  | 2008-350T16:43:00 |  | 000T00:40:00 | 2008-350T17:23:00 | ISS_NAC to Saturn | POS_Z to NSP | SP Turn to Waypoint
ISS_097TI_MR3CLD350_PRIME | C, U | 2008-350T17:23:00 | E097_MR3CLD350+000T00:00:00 | 000T01:15:00 | 2008-350T18:38:00 | ISS_NAC to Titan | NEG_X to Sun
CAPS_097SA_SURVEYPTG002_PRIME |  | 2008-350T18:38:00 |  | 000T02:00:00 | 2008-350T20:38:00 | POS_Y to COROT | PIC
CIRS_097SA_REGMAP001_PRIME |  | 2008-350T20:38:00 |  | 000T02:30:00 | 2008-350T23:08:00 | CIRS_FPB to Saturn | POS_Z to NSP
SP_097EA_DLTURN450_PRIME |  | 2008-350T23:08:00 |  | 000T00:40:00 | 2008-350T23:48:00 | XBAND to Earth | POS_X to NEP
SP_097EA_M34BWGNON351_PRIME | C, E | 2008-350T23:48:00 |  | 000T09:00:00 | 2008-351T08:48:00 | XBAND to Earth | 3_Hr_Rolling | POS_X to NEP
SP_097SA_WAYPTTURN351_PRIME |  | 2008-351T08:48:00 |  | 000T00:40:00 | 2008-351T09:28:00 | ISS_NAC to Saturn | NEG_X to Sun | SP Turn to Waypoint
NEW WAYPOINT |  | 2008-351T09:28:00 |  | 003T00:10:00 | 2008-354T09:38:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_097RI_GAMCRUOCC012_PRIME |  | 2008-351T09:28:00 |  | 000T04:27:00 | 2008-351T13:55:00 | VIMS_IR to 187.791/-57.113 | NEG_X to Sun
VIMS_097SA_NPOLEDYN001_PRIME | I, U | 2008-351T13:55:00 |  | 000T04:42:00 | 2008-351T18:37:00 | ISS_NAC to Saturn | NEG_X to NSP
UVIS_097ST_ALPCRUSA002_PRIME | I | 2008-351T18:37:00 |  | 000T01:32:00 | 2008-351T20:09:00 | UVIS_FUV to 186.65/-63.099 (0.082,0.0,0.0 deg. offset) | NEG_Z to NSP
VIMS_097SA_NPOLEDYN002_PRIME | I, U | 2008-351T20:09:00 |  | 000T02:09:00 | 2008-351T22:18:00 | ISS_NAC to Saturn | NEG_X to NSP
UVIS_097ST_BETCENSA001_PRIME | I | 2008-351T22:18:00 |  | 000T01:30:00 | 2008-351T23:48:00 | UVIS_FUV to 210.956/-60.373 (0.082,0.0,0.0 deg. offset) | NEG_Z to NSP
VIMS_097SA_NPOLEDYN003_PRIME | I, R, U | 2008-351T23:48:00 |  | 000T02:42:00 | 2008-352T02:30:00 | ISS_NAC to Saturn | NEG_X to NSP
RADAR_097SA_NORTHPOL001_PRIME | M | 2008-352T02:30:00 |  | 000T07:00:00 | 2008-352T09:30:00 | NEG_Z to Saturn | PIC
ISS_097RH_020W151PH001_PRIME | C, M, U, V | 2008-352T09:30:00 |  | 000T02:13:00 | 2008-352T11:43:00 | UVIS_FUV to Rhea | NEG_X to Sun | Do (0,0,-1.03 mrad) offset for CIRS FP3 within the first approx. 10 percent of the tracking period (but at least for 5 min.)
ISS_097SA_LIMBSCAN001_PRIME | M, V | 2008-352T11:43:00 |  | 000T00:45:00 | 2008-352T12:28:00 | ISS_NAC to Saturn | POS_X to NEP | Observe night limb for MAPS Titan vertical profile.
NAV_097SK_OPNAV521_PRIME | M | 2008-352T12:28:00 |  | 000T01:29:00 | 2008-352T13:57:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_097EA_DLTURN521_PRIME | M | 2008-352T13:57:00 |  | 000T00:01:00 | 2008-352T13:58:00 | XBAND to Earth | NEG_X to 261.5/-15.1
SP_097EA_C70METOTP352_PRIME | C, M, N | 2008-352T13:58:00 |  | 000T09:00:00 | 2008-352T22:58:00 | XBAND to Earth | NEG_X to 261.5/-15.1 | CDA vertical ring plane crossing
Periapse R = 5.765 Rs, lat ... |  | 2008-352T17:25:26 |  | 000T00:00:01 | 2008-352T17:25:27
SP_097SA_WAYPTTURN352_PRIME | M, R | 2008-352T22:58:00 |  | 000T00:40:00 | 2008-352T23:38:00 | ISS_NAC to Saturn | NEG_X to Sun | SP Turn to Waypoint
VIMS_097SA_SPOLEHIRE001_PRIME | M, R | 2008-352T23:38:00 |  | 000T01:20:00 | 2008-353T00:58:00 | ISS_NAC to Saturn | NEG_X to NSP
RADAR_097SA_SOUTHPOL001_PRIME | M | 2008-353T00:58:00 |  | 000T07:00:00 | 2008-353T07:58:00 | NEG_Z to Saturn | PIC
VIMS_097SA_SPOLEDYN001_PRIME | I, U | 2008-353T07:58:00 |  | 000T14:50:00 | 2008-353T22:48:00 | ISS_NAC to Saturn | NEG_X to NSP
ISS_097OT_SATELLORB008_PRIME |  | 2008-353T22:48:00 |  | 000T00:30:00 | 2008-353T23:18:00 | ISS_NAC to Rocks | NEG_X to Sun
SP_097EA_DLTURN353_PRIME |  | 2008-353T23:18:00 |  | 000T00:40:00 | 2008-353T23:58:00 | XBAND to Earth | NEG_X to 261.5/-15.1
SP_097EA_M70METOTB353_PRIME | C, N | 2008-353T23:58:00 |  | 000T09:00:00 | 2008-354T08:58:00 | XBAND to Earth | 5_Hr_Rolling
SP_097SA_WAYPTTURN354_PRIME |  | 2008-354T08:58:00 |  | 000T00:40:00 | 2008-354T09:38:00 | ISS_NAC to Saturn | NEG_X to NSP | SP Turn to Waypoint
NEW WAYPOINT |  | 2008-354T09:38:00 |  | 001T07:31:00 | 2008-355T17:09:00 | ISS_NAC to Saturn | NEG_X to NSP
ISS_097TI_MR1CLDF354_PRIME | C, U | 2008-354T09:38:00 | E097_MR1CLDF354+000T00:00:00 | 000T01:15:00 | 2008-354T10:53:00 | ISS_NAC to Titan | NEG_Z to Sun
CIRS_097SA_FIRMAP002_PRIME |  | 2008-354T10:53:00 |  | 000T22:00:00 | 2008-355T08:53:00 | CIRS_FP1 to Saturn | NEG_X to NSP
SP_097EA_DLTURN355_PRIME |  | 2008-355T08:53:00 |  | 000T00:40:00 | 2008-355T09:33:00 | XBAND to Earth | NEG_X to NEP
SP_097EA_G70METNON355_PRIME | C | 2008-355T09:33:00 |  | 000T06:56:00 | 2008-355T16:29:00 | XBAND to Earth | NEG_X to NEP | no rolling, CIRS pre-TOST
Titan Flyby T49 Segment |  | 2008-355T16:29:00 |  | 002T05:45:00 | 2008-357T22:14:00
SP_097TI_WAYPTTURN355_PRIME |  | 2008-355T16:29:00 |  | 000T00:40:00 | 2008-355T17:09:00 | NEG_Y to Titan (0.0,-15.0,0.0 deg. offset) | NEG_Z to 340.0/0.0
NEW WAYPOINT |  | 2008-355T17:09:00 |  | 002T05:45:00 | 2008-357T22:54:00 | NEG_Y to Titan (0.0,-15.0,0.0 deg. offset) | NEG_Z to 340.0/0.0
SP_097TI_DEADTIME355_PRIME |  | 2008-355T17:09:00 |  | 000T00:15:32 | 2008-355T17:24:32 | NEG_Y to Titan | NEG_X to Sun
CIRS_097TI_MIDIRTMAP001_PRIME | I, V | 2008-355T17:24:32 | GMB_E097_Titan49-000T19:35:20 | 000T06:35:20 | 2008-355T23:59:52 | CIRS_FPB to Titan | POS_X to North_Pole_Dir
CIRS_097TI_FIRNADCMP001_PRIME | C, I, U, V | 2008-355T23:59:52 | GMB_E097_Titan49-000T13:00:00 | 000T04:00:00 | 2008-356T03:59:52 | CIRS_FP1 to Titan | PIC
ISS_097TI_GLOBMAP001_PRIME | C, V | 2008-356T03:59:52 | GMB_E097_Titan49-000T09:00:00 | 000T04:00:00 | 2008-356T07:59:52 | ISS_NAC to Titan | NEG_X to Sun
ISS_097TI_REGMAP001_PRIME | C, V | 2008-356T07:59:52 | GMB_E097_Titan49-000T05:00:00 | 000T02:00:00 | 2008-356T09:59:52 | ISS_NAC to Titan | NEG_X to Sun
CIRS_097TI_FIRLMBINT001_PRIME | C, I, R, U, V | 2008-356T09:59:52 | GMB_E097_Titan49-000T03:00:00 | 000T01:00:00 | 2008-356T10:59:52 | CIRS_FP1 to Titan | PIC
VIMS_097TI_GLOBMAP001_PRIME | C, I, M, R | 2008-356T10:59:52 | GMB_E097_Titan49-000T02:00:00 | 000T01:14:00 | 2008-356T12:13:52 | VIMS_IR to Titan | NEG_X to Sun
ENGR_097SC_RADRCS356_PRIME | M, R | 2008-356T12:13:52 | GMB_E097_Titan49-000T00:46:00 | 000T00:01:00 | 2008-356T12:14:52 | NEG_Y to Titan (0.0,-15.0,0.0 deg. offset) | NEG_Z to 340.0/0.0 | DB (.5,.5,2)
VIMS_097TI_TRANS001_PRIME | M, R | 2008-356T12:14:52 | GMB_E097_Titan49-000T00:45:00 | 000T00:21:00 | 2008-356T12:35:52 | VIMS_IR to Titan | NEG_X to Sun
RADAR_097TI_T49INSAR001_PRIME | M | 2008-356T12:35:52 | GMB_E097_Titan49-000T00:24:00 | 000T00:15:00 | 2008-356T12:50:52 | NEG_Z to Titan | NEG_X to Titan_SC_RAM
Start of T49 Dual Playback ... |  | 2008-356T12:36:52 | GMB_E097_Titan49-000T00:23:00 | 000T00:00:01 | 2008-356T12:36:53
RADAR_097TI_T49CAALT001_PRIME | M | 2008-356T12:50:52 | GMB_E097_Titan49-000T00:09:00 | 000T00:05:00 | 2008-356T12:55:52 | NEG_Z to Titan | NEG_X to Titan_SC_RAM
RADAR_097TI_T49OUTSAR001_PRIME | M | 2008-356T12:55:52 | GMB_E097_Titan49-000T00:04:00 | 000T00:22:00 | 2008-356T13:17:52 | NEG_Z to Titan | NEG_X to Titan_SC_RAM
97TI (t) T49 TITAN Outbou... |  | 2008-356T12:59:52 |  | 000T00:00:01 | 2008-356T12:59:53
Apoapse Per = 9.4 d, inc =... |  | 2008-356T13:04:11 |  | 000T00:00:01 | 2008-356T13:04:12
End of T49 Dual Playback pe... |  | 2008-356T13:17:52 | GMB_E097_Titan49+000T00:18:00 | 000T00:00:01 | 2008-356T13:17:53
RADAR_098TI_T49OUTALT001_PRIME | M | 2008-356T13:17:52 | GMB_E097_Titan49+000T00:18:00 | 000T00:12:00 | 2008-356T13:29:52 | NEG_Z to Titan (0.0,0.0,-58.0 deg. offset) | NEG_X to NTP
RADAR_098TI_T49OHISAR001_PRIME | M | 2008-356T13:29:52 | GMB_E097_Titan49+000T00:30:00 | 000T00:20:00 | 2008-356T13:49:52 | NEG_Z to Titan (0.0,0.0,-58.0 deg. offset) | NEG_X to NTP
ENGR_098SA_RADRWBIAS356_PPS | M | 2008-356T13:49:52 | GMB_E097_Titan49+000T00:50:00 | 000T00:21:14 | 2008-356T14:11:06 | NEG_Y to Titan (0.0,-15.0,0.0 deg. offset) | NEG_Z to 340.0/0.0 | Deadband = (.5,.5,2)
RADAR_098TI_T49OUTSCT001_PRIME | M | 2008-356T14:11:06 | GMB_E097_Titan49+000T01:11:14 | 000T00:48:46 | 2008-356T14:59:52 | NEG_Z to Titan (0.0,0.0,-58.0 deg. offset) | NEG_X to NTP
RADAR_098TI_T49OUTRAD001_PRIME | M | 2008-356T14:59:52 | GMB_E097_Titan49+000T02:00:00 | 000T03:30:00 | 2008-356T18:29:52 | NEG_Z to Titan (0.0,0.0,-58.0 deg. offset) | NEG_X to NTP | Use -X_NTP and -Y_NTP for the 2ndary with (0,0,-58 deg) offset for the two polarizations.
CIRS_098TI_MIRLMBINT001_PRIME | C, I, U, V | 2008-356T18:29:52 | GMB_E097_Titan49+000T05:30:00 | 000T03:30:00 | 2008-356T21:59:52 | CIRS_FPB to Titan | PIC
VIMS_098TI_CLOUDMAP001_PRIME | C, I | 2008-356T21:59:52 | GMB_E097_Titan49+000T09:00:00 | 000T04:00:00 | 2008-357T01:59:52 | VIMS_IR to Titan | NEG_X to Sun
ISS_098TI_NIGHTNAC001_PRIME | C, V | 2008-357T01:59:52 | GMB_E097_Titan49+000T13:00:00 | 000T00:30:00 | 2008-357T02:29:52 | ISS_NAC to Titan | NEG_X to Sun
CIRS_098TI_MIDIRTMAP002_PRIME | C, I, V | 2008-357T02:29:52 | GMB_E097_Titan49+000T13:30:00 | 000T03:30:00 | 2008-357T05:59:52 | CIRS_FPB to Titan | POS_X to North_Pole_Dir
ISS_098TI_LRMONITOR001_PRIME | C, V | 2008-357T05:59:52 | GMB_E097_Titan49+000T17:00:00 | 000T00:30:00 | 2008-357T06:29:52 | ISS_NAC to Titan | NEG_X to Sun
SP_098TI_DEADTIME357_PRIME |  | 2008-357T06:29:52 | GMB_E097_Titan49+000T17:30:00 | 000T00:04:08 | 2008-357T06:34:00 | NEG_Y to Titan | NEG_X to Sun
SP_098EA_DLTURN357_PRIME |  | 2008-357T06:34:00 |  | 000T00:40:00 | 2008-357T07:14:00 | XBAND to Earth | NEG_X to NEP
SP_098EA_G70METNON357_PRIME | C | 2008-357T07:14:00 |  | 000T09:00:00 | 2008-357T16:14:00 | XBAND to Earth | Rolling/Bias
SP_098EA_C70ARRNON357_PRIME | C | 2008-357T16:14:00 |  | 000T02:00:00 | 2008-357T18:14:00 | XBAND to Earth | NEG_X to NEP | DSCAL over dual playback
SP_098EA_C34HEFNON357_PRIME | C | 2008-357T18:14:00 |  | 000T04:00:00 | 2008-357T22:14:00 | XBAND to Earth | NEG_X to NEP | DSCAL over dual playback
RINGS_98 Segment |  | 2008-357T22:14:00 |  | 005T17:46:00 | 2008-363T16:00:00
SP_098SA_WAYPTTURN357_PRIME |  | 2008-357T22:14:00 |  | 000T00:40:00 | 2008-357T22:54:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-357T22:54:00 |  | 005T18:21:00 | 2008-363T17:15:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_098RI_TMAPN30LP001_PRIME | C, I, U | 2008-357T22:54:00 |  | 000T07:40:00 | 2008-358T06:34:00 | CIRS_FP1 to Rings | NEG_X to Sun
SP_098EA_DLTURN358_PRIME |  | 2008-358T06:34:00 |  | 000T00:40:00 | 2008-358T07:14:00 | XBAND to Earth | POS_X to NEP
SP_098EA_G34HEFNON358_PRIME | C | 2008-358T07:14:00 |  | 000T09:00:00 | 2008-358T16:14:00 | XBAND to Earth | Rolling/Bias | POS_X to NEP
SP_098SA_WAYPTTURN358_PRIME |  | 2008-358T16:14:00 |  | 000T00:40:00 | 2008-358T16:54:00 | ISS_NAC to Saturn | NEG_X to Sun
CAPS_098SA_SURVEYPTG006_PRIME |  | 2008-358T16:54:00 |  | 000T01:06:00 | 2008-358T18:00:00 | ISS_NAC to Saturn (45.0,0.0,0.0 deg. offset) | NEG_X to Sun
ISS_098OT_SATELLORB007_PRIME |  | 2008-358T18:00:00 |  | 000T00:30:00 | 2008-358T18:30:00 | ISS_NAC to Rocks | NEG_X to Sun
CIRS_098RI_TMAPN45LP001_PRIME | C, R, U | 2008-358T18:30:00 |  | 000T04:00:00 | 2008-358T22:30:00 | CIRS_FP1 to Rings | NEG_X to Sun
RADAR_098TI_NMIDLCAL006_PRIME |  | 2008-358T22:30:00 |  | 000T01:30:00 | 2008-359T00:00:00 | NEG_Z to Titan (0.0,0.0,-3.0 deg. offset) | POS_Y to Sun
UVIS_098ST_URDELCEN001_PRIME | C, I, M | 2008-359T00:00:00 |  | 000T04:21:00 | 2008-359T04:21:00 | UVIS_FUV to 182.089/-50.722 | POS_X to L_ANSA_A
CAPS_098SA_SURVEYPTG002_PRIME | M | 2008-359T04:21:00 |  | 000T02:00:00 | 2008-359T06:21:00 | POS_Z to Saturn (0.0,0.0,12.0 deg. offset) | POS_X to NSP
ISS_098OT_SATELLORB006_PRIME |  | 2008-359T06:21:00 |  | 000T01:04:00 | 2008-359T07:25:00 | ISS_NAC to Rocks | NEG_X to Sun
UVIS_098ST_URBETCRU001_PRIME | C, I | 2008-359T07:25:00 |  | 000T05:15:00 | 2008-359T12:40:00 | UVIS_FUV to 191.93/-59.689 | POS_X to L_ANSA_A
ISS_098OT_SATELLORB008_PRIME |  | 2008-359T12:40:00 |  | 000T00:24:00 | 2008-359T13:04:00 | ISS_NAC to Rocks | NEG_X to Sun
SP_098EA_DLTURN359_PRIME |  | 2008-359T13:04:00 |  | 000T00:40:00 | 2008-359T13:44:00 | XBAND to Earth | NEG_Y to 65.0/73.0
SP_098EA_C70METOTP359_PRIME | C, N | 2008-359T13:44:00 |  | 000T09:00:00 | 2008-359T22:44:00 | XBAND to Earth | NEG_Y to 65.0/73.0 | No Roll due to SCO Waiver and SRU Violation. Secondary chosen by MIMI and CDA. SRU Score = 0.
SP_098SA_WAYPTTURN359_PRIME |  | 2008-359T22:44:00 |  | 000T00:40:00 | 2008-359T23:24:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_098RI_VTMPN60MP001_PRIME | C, U | 2008-359T23:24:00 |  | 000T06:12:00 | 2008-360T05:36:00 | CIRS_FP1 to Rings | NEG_X to Sun
UVIS_098ST_URALPARA001_PRIME | C, I | 2008-360T05:36:00 |  | 000T07:00:00 | 2008-360T12:36:00 | UVIS_FUV to 262.96/-49.876 | NEG_X to Sun
ISS_098RI_SHRTMOV001_PRIME | C, V | 2008-360T12:36:00 |  | 000T08:00:00 | 2008-360T20:36:00 | ISS_NAC to Rings | PIC
CIRS_098RI_TDIFN20HP001_PRIME | C, I, M, U | 2008-360T20:36:00 |  | 000T05:00:00 | 2008-361T01:36:00 | CIRS_FP1 to Rings | NEG_X to Sun
SP_098EA_DLTURN361_PRIME | M | 2008-361T01:36:00 |  | 000T00:33:00 | 2008-361T02:09:00 | XBAND to Earth | POS_X to NEP | First Turn of Two Part Turn.
SP_098EA_M70METNON561_PRIME | M | 2008-361T02:09:00 |  | 000T04:15:00 | 2008-361T06:24:00 | XBAND to Earth | POS_X to 128.44/-82.73 | Secondary was chosen for CAPS.
SP_098EA_RWDTURN361_PRIME | M | 2008-361T02:09:00 |  | 000T00:25:00 | 2008-361T02:34:00 | XBAND to Earth | POS_X to 128.44/-82.73 | Second Turn of Two Part Turn. This turn overlaps the downlink. This is acceptable, because this turn is simply a roll about the Z-axis.
Periapse R = 9.095 Rs, lat ... |  | 2008-361T05:10:51 |  | 000T00:00:01 | 2008-361T05:10:52
SP_098EA_RWDTURN561_PRIME | M | 2008-361T05:59:00 |  | 000T00:25:00 | 2008-361T06:24:00 | XBAND to Earth | POS_X to NEP | First Turn of Two Part Turn. This turn overlaps the downlink. This is acceptable, because this turn is simply a roll about the Z-axis.
SP_098SA_WAYPTTURN361_PRIME | M | 2008-361T06:24:00 |  | 000T00:33:00 | 2008-361T06:57:00 | ISS_NAC to Saturn | NEG_X to Sun | Second Turn of Two Part Turn
ISS_098EN_PLMMRHP001_PRIME | C, M, U, V | 2008-361T06:57:00 |  | 000T03:00:00 | 2008-361T09:57:00 | ISS_NAC to Enceladus | PIC
CIRS_098RI_TDIFS20HP001_PRIME | M, U | 2008-361T09:57:00 |  | 000T03:00:00 | 2008-361T12:57:00 | CIRS_FP1 to Rings | NEG_X to Sun
VIMS_098RI_COMPHILIT120_PRIME | C, U | 2008-361T12:57:00 |  | 000T03:30:00 | 2008-361T16:27:00 | VIMS_IR to Rings | POS_Z to NSP
CIRS_098RI_VENCLSHP001_PRIME | C, U | 2008-361T16:27:00 |  | 000T05:32:00 | 2008-361T21:59:00 | CIRS_FP1 to Rings | NEG_X to Sun
NAV_098SK_OPNAV611_PRIME |  | 2008-361T21:59:00 |  | 000T01:29:00 | 2008-361T23:28:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_098EA_DLTURN611_PRIME |  | 2008-361T23:28:00 |  | 000T00:01:00 | 2008-361T23:29:00 | XBAND to Earth | NEG_Y to 50.0/80.0
SP_098EA_M70METOTB361_PRIME | C, N | 2008-361T23:29:00 |  | 000T09:00:00 | 2008-362T08:29:00 | XBAND to Earth | NEG_Y to 50.0/80.0 | No Roll due to SCO Waiver and SRU Violation. Secondary chosen by MIMI and CDA. SRU Score = 0.
SP_098SA_WAYPTTURN362_PRIME |  | 2008-362T08:29:00 |  | 000T00:40:00 | 2008-362T09:09:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_098RI_SHADLMP001_PRIME | C | 2008-362T09:09:00 |  | 000T21:11:00 | 2008-363T06:20:00 | CIRS_FP1 to Rings | NEG_X to Sun
SP_098EA_DLTURN368_PRIME |  | 2008-363T06:20:00 |  | 000T00:40:00 | 2008-363T07:00:00 | XBAND to Earth | POS_X to NEP
SP_098EA_G34HEFNON363_PRIME | C | 2008-363T07:00:00 |  | 000T09:00:00 | 2008-363T16:00:00 | XBAND to Earth | 5_Hr_Rolling | POS_X to NEP; 6 hr roll, 3 hr dscal
SATURN_98_100 Segment |  | 2008-363T16:00:00 |  | 011T23:16:00 | 2009-009T15:16:00
NAV_098SK_OPNAV631_PRIME |  | 2008-363T16:00:00 |  | 000T01:14:00 | 2008-363T17:14:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Earth point, end at new Waypoint
NAV_098SK_WAYPTTURN631_PRIME |  | 2008-363T17:14:00 |  | 000T00:01:00 | 2008-363T17:15:00 | ISS_NAC to Saturn | NEG_X to Sun
NEW WAYPOINT |  | 2008-363T17:15:00 |  | 011T22:01:00 | 2009-009T15:16:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_098SA_1X2WP25001_PRIME |  | 2008-363T17:15:00 |  | 000T01:00:00 | 2008-363T18:15:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_098TI_MR3CLD363_PRIME | C, U | 2008-363T18:15:00 | E098_MR3CLD363+000T00:00:00 | 000T01:15:00 | 2008-363T19:30:00 | ISS_NAC to Titan | NEG_Z to Sun
CAPS_098SA_SURVEYPTG004_PRIME |  | 2008-363T19:30:00 |  | 000T02:00:00 | 2008-363T21:30:00 | NEG_Z to Saturn (0.0,0.0,12.0 deg. offset) | NEG_X to North_Pole_Dir
MAG_098SU_CALROLL001_PRIME |  | 2008-363T21:30:00 |  | 000T06:15:00 | 2008-364T03:45:00 | NEG_X to Sun (0.0,0.0,-30.0 deg. offset) | Rolling
ISS_098SA_1X2WP25002_PRIME |  | 2008-364T03:45:00 |  | 000T01:00:00 | 2008-364T04:45:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_098SA_FIRMAP001_PRIME |  | 2008-364T04:45:00 |  | 000T19:05:00 | 2008-364T23:50:00 | CIRS_FP1 to Saturn | NEG_X to NSP
SP_098EA_DLTURN364_PRIME |  | 2008-364T23:50:00 |  | 000T00:25:00 | 2008-365T00:15:00 | XBAND to Earth | NEG_Y to 79.54/35.12 | SP Turn to Earth
SP_098EA_M34BWGNON365_PRIME | C | 2008-365T00:15:00 |  | 000T09:00:00 | 2008-365T09:15:00 | XBAND to Earth | NEG_Y to 79.54/35.12 | MIMI NEG_Y to Saturn (0,0, -9.5)
SP_098SA_WAYPTTURN365_PRIME |  | 2008-365T09:15:00 |  | 000T00:40:00 | 2008-365T09:55:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_098TI_MR3CLD365_PRIME | C, U | 2008-365T09:55:00 | E098_MR3CLD365+000T00:00:00 | 000T01:15:00 | 2008-365T11:10:00 | ISS_NAC to Titan | NEG_Z to Sun
ISS_098OT_SATELLORB014_PRIME |  | 2008-365T11:10:00 |  | 000T00:30:00 | 2008-365T11:40:00 | ISS_NAC to Rocks | NEG_X to Sun
ISS_098SA_1X2WP25004_PRIME |  | 2008-365T11:40:00 |  | 000T01:00:00 | 2008-365T12:40:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_098SA_COMPSIT002_PRIME | U | 2008-365T12:40:00 |  | 000T06:00:00 | 2008-365T18:40:00 | CIRS_FP1 to Saturn | POS_Z to NSP
UVIS_098SA_EUVFUV001_PRIME | I | 2008-365T18:40:00 |  | 000T09:25:00 | 2008-366T04:05:00 | UVIS_FUV to Saturn (1.148,0.0,3.21 deg. offset) | POS_Z to NSP
Apoapse Per = 9.6 d, inc =... |  | 2008-366T00:06:10 |  | 000T00:00:01 | 2008-366T00:06:11
ISS_099DI_088W008PH001_PRIME | C, U, V | 2008-366T04:05:00 |  | 000T02:00:00 | 2008-366T06:05:00 | UVIS_FUV to Dione | NEG_X to Sun | Do (0,0,-1.03 mrad) offset for CIRS FP3 within the first approx. 10 percent of the tracking period (but at least for 5 min.)
SP_099EA_DLTURN366_PRIME |  | 2008-366T06:05:00 |  | 000T00:40:00 | 2008-366T06:45:00 | XBAND to Earth | POS_X to NEP | SP Turn to Earth
SP_099EA_G34BWGNON366_PRIME | C, R | 2008-366T06:45:00 |  | 000T09:00:00 | 2008-366T15:45:00 | XBAND to Earth | 6_Hr_Rolling | POS_X to NEP
SP_099SA_WAYPTTURN366_PRIME |  | 2008-366T15:45:00 |  | 000T00:40:00 | 2008-366T16:25:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_099TI_MR3CLD366_PRIME | C, U | 2008-366T16:25:00 | E099_MR3CLD366+000T00:00:00 | 000T01:15:00 | 2008-366T17:40:00 | ISS_NAC to Titan | NEG_Z to Sun
VIMS_099SU_SOLARPORT001_PRIME | U | 2008-366T17:40:00 |  | 000T08:00:00 | 2009-001T01:40:00 | VIMS_IR_SOL to Sun | NEG_X to NSP
CAPS_099SA_SURVEYPTG002_PRIME |  | 2009-001T01:40:00 |  | 000T02:00:00 | 2009-001T03:40:00 | POS_X to North_Pole_Dir (0.0,0.0,12.0 deg. offset) | POS_Z to Saturn
ISS_099SA_1X2WP25003_PRIME |  | 2009-001T03:40:00 |  | 000T01:00:00 | 2009-001T04:40:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_099SA_FIRMAP001_PRIME | V | 2009-001T04:40:00 |  | 000T13:18:00 | 2009-001T17:58:00 | CIRS_FP1 to Saturn | POS_X to NSP
ISS_099SA_1X2WP25004_PRIME |  | 2009-001T17:58:00 |  | 000T01:00:00 | 2009-001T18:58:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_099OT_PLEIADES001_PRIME |  | 2009-001T18:58:00 |  | 000T09:17:00 | 2009-002T04:15:00 | VIMS_IR to 56.75/24.12 | NEG_X to 343.11/-32.38 | Secondary axis required by MIMI agreed to:Neg X to 343.11/-32.38, KHB, 02/11/08
ISS_099SA_1X2WP25015_PRIME |  | 2009-002T04:15:00 |  | 000T01:00:00 | 2009-002T05:15:00 | ISS_NAC to Saturn | NEG_Z to NSP
NAV_099SK_OPNAV021_PRIME |  | 2009-002T05:15:00 |  | 000T01:29:00 | 2009-002T06:44:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_099EA_DLTURN021_PRIME |  | 2009-002T06:44:00 |  | 000T00:01:00 | 2009-002T06:45:00 | XBAND to Earth | POS_X to NEP
SP_099EA_G70METNON002_PRIME | C, M | 2009-002T06:45:00 |  | 000T09:00:00 | 2009-002T15:45:00 | XBAND to Earth | 6_Hr_Rolling | POS_X to NEP; 6 hr roll, 3 hr dscal
SP_099SA_WAYPTTURN002_PRIME | M | 2009-002T15:45:00 |  | 000T00:40:00 | 2009-002T16:25:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_099TI_MR2CLD002_PRIME | C, M, U | 2009-002T16:25:00 | E099_MR2CLD002+000T00:00:00 | 000T01:15:00 | 2009-002T17:40:00 | ISS_NAC to Titan | NEG_Z to Sun
VIMS_099SA_NPOLEDYN001_PRIME | I, M, U | 2009-002T17:40:00 |  | 000T10:11:00 | 2009-003T03:51:00 | ISS_NAC to Saturn | NEG_X to NSP
UVIS_099ST_BETCRU002_PRIME |  | 2009-003T03:51:00 |  | 000T01:30:00 | 2009-003T05:21:00 | UVIS_FUV to 191.93/-59.688 (0.258,0.0,0.0 deg. offset) | NEG_Z to NSP
VIMS_099SA_NPOLEDYN003_PRIME | I, U | 2009-003T05:21:00 |  | 000T17:00:00 | 2009-003T22:21:00 | ISS_NAC to Saturn | NEG_X to NSP
SP_099EA_DLTURN003_PRIME |  | 2009-003T22:21:00 |  | 000T00:40:00 | 2009-003T23:01:00 | XBAND to Earth | POS_X to NEP | SP Turn to Earth
SP_099EA_M70METSEQ003_PRIME | C | 2009-003T23:01:00 |  | 000T09:00:00 | 2009-004T08:01:00 | XBAND to Earth | Rolling/SRU | POS_X to NEP
SP_099SA_WAYPTTURN004_PRIME |  | 2009-004T08:01:00 |  | 000T00:25:00 | 2009-004T08:26:00 | ISS_NAC to Saturn | NEG_X to Sun
UVIS_099SA_AURORA001_PRIME | I, V | 2009-004T08:26:00 |  | 000T03:51:00 | 2009-004T12:17:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_099TE_064W150PH001_PRIME | C, U, V | 2009-004T12:17:00 |  | 000T03:08:00 | 2009-004T15:25:00 | UVIS_FUV to Tethys | NEG_X to Sun | Do (0,0,-1.03 mrad) offset for CIRS FP3 within the first approx. 10 percent of the tracking period (but at least for 5 min.)
CAPS_099SA_IMVP9PTG001_PRIME | M | 2009-004T15:25:00 |  | 000T08:40:00 | 2009-005T00:05:00 | POS_Y to COROT (0.0,0.0,20.0 deg. offset) | POS_X to NSP
Periapse R = 9.100 Rs, lat ... |  | 2009-004T19:01:09 |  | 000T00:00:01 | 2009-004T19:01:10
VIMS_099SA_SPOLEDYN001_PRIME | I, U | 2009-005T00:05:00 |  | 000T11:00:00 | 2009-005T11:05:00 | ISS_NAC to Saturn | NEG_X to NSP
SP_099EA_DLTURN005_PRIME |  | 2009-005T11:05:00 |  | 000T00:30:00 | 2009-005T11:35:00 | XBAND to Earth | NEG_Y to 75.0/57.0 | SP Turn to Earth
SP_099EA_G70METNON005_PRIME |  | 2009-005T11:35:00 |  | 000T03:55:00 | 2009-005T15:30:00 | XBAND to Earth | NEG_Y to 75.0/57.0 | NEG_Y to 75.0/57.0 for CAPS
SP_099SA_WAYPTTURN005_PRIME |  | 2009-005T15:30:00 |  | 000T00:35:00 | 2009-005T16:05:00 | ISS_NAC to Saturn | NEG_X to Sun
VIMS_099SA_SPOLEDYN002_PRIME | I, U | 2009-005T16:05:00 |  | 000T13:11:00 | 2009-006T05:16:00 | ISS_NAC to Saturn | NEG_X to NSP
NAV_099SK_OPNAV061_PRIME |  | 2009-006T05:16:00 |  | 000T01:14:00 | 2009-006T06:30:00 | ISS_NAC to Satellites | POS_Z to NSP | Start at Waypoint, end at Earth point
NAV_099EA_DLTURN061_PRIME |  | 2009-006T06:30:00 |  | 000T00:01:00 | 2009-006T06:31:00 | XBAND to Earth | NEG_X to NEP
SP_099EA_G70METSEQ006_PRIME | C | 2009-006T06:31:00 |  | 000T09:00:00 | 2009-006T15:31:00 | XBAND to Earth | 5_Hr_Rolling | NEG_X to NEP; 5 hr roll (SID suspend), 4 hr dscal
SP_099SA_WAYPTTURN006_PRIME |  | 2009-006T15:31:00 |  | 000T00:40:00 | 2009-006T16:11:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_099TI_MR2HAZ006_PRIME | C, U | 2009-006T16:11:00 | E099_MR2HAZ006+000T00:00:00 | 000T01:15:00 | 2009-006T17:26:00 | ISS_NAC to Titan | NEG_X to Sun
ISS_099SA_1X2WP25007_PRIME |  | 2009-006T17:26:00 |  | 000T01:00:00 | 2009-006T18:26:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_099SA_COMPSIT001_PRIME | U, V | 2009-006T18:26:00 |  | 000T11:10:00 | 2009-007T05:36:00 | CIRS_FP1 to Saturn | POS_Z to NSP
SP_099EA_DLTURN007_PRIME | U | 2009-007T05:36:00 |  | 000T00:40:00 | 2009-007T06:16:00 | XBAND to Earth | NEG_X to NEP | SP Turn to Earth
SP_099EA_G34BWGSEQ007_PRIME | C | 2009-007T06:16:00 |  | 000T09:00:00 | 2009-007T15:16:00 | XBAND to Earth | Rolling/SRU | NEG_X to NEP
SP_099SA_WAYPTTURN007_PRIME | R | 2009-007T15:16:00 |  | 000T00:40:00 | 2009-007T15:56:00 | ISS_NAC to Saturn | NEG_X to Sun
CAPS_099SA_SURVEYPTG004_PRIME | R | 2009-007T15:56:00 |  | 000T02:00:00 | 2009-007T17:56:00 | NEG_Z to Saturn (0.0,10.0,14.0 deg. offset) | NEG_X to North_Pole_Dir
RADAR_099TI_SMIDLCAL001_PRIME |  | 2009-007T17:56:00 |  | 000T01:30:00 | 2009-007T19:26:00 | NEG_Z to Titan (0.0,0.0,-3.0 deg. offset) | POS_Y to Sun
ISS_099SA_1X2WP25008_PRIME |  | 2009-007T19:26:00 |  | 000T01:00:00 | 2009-007T20:26:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_099SA_COMPSIT003_PRIME | V | 2009-007T20:26:00 |  | 000T08:00:00 | 2009-008T04:26:00 | CIRS_FP1 to Saturn | POS_Z to NSP
ISS_099RI_MNRNGSHAD010_PRIME |  | 2009-008T04:26:00 |  | 000T01:10:00 | 2009-008T05:36:00 | ISS_NAC to Rings | PIC
SP_099EA_DLTURN008_PRIME |  | 2009-008T05:36:00 |  | 000T00:40:00 | 2009-008T06:16:00 | XBAND to Earth | NEG_X to NEP | SP Turn to Earth
SP_099EA_G34BWGSEQ008_PRIME | C | 2009-008T06:16:00 |  | 000T09:00:00 | 2009-008T15:16:00 | XBAND to Earth | 6_Hr_Rolling | NEG_X to NEP; 6 hr roll, 3 hr dscal
SP_099SA_WAYPTTURN008_PRIME |  | 2009-008T15:16:00 |  | 000T00:40:00 | 2009-008T15:56:00 | ISS_NAC to Saturn | NEG_X to Sun
ISS_099OT_SATELLORB015_PRIME |  | 2009-008T15:56:00 |  | 000T00:30:00 | 2009-008T16:26:00 | ISS_NAC to Rocks | NEG_X to Sun
ISS_099SA_1X2WP25011_PRIME |  | 2009-008T16:26:00 |  | 000T01:00:00 | 2009-008T17:26:00 | ISS_NAC to Saturn | NEG_X to Sun
CIRS_099SA_COMPSIT002_PRIME |  | 2009-008T17:26:00 |  | 000T11:10:00 | 2009-009T04:36:00 | CIRS_FP1 to Saturn | POS_Z to NSP
ISS_099SA_1X2WP25013_PRIME |  | 2009-009T04:36:00 |  | 000T01:00:00 | 2009-009T05:36:00 | ISS_NAC to Saturn | NEG_X to Sun
SP_099EA_DLTURN009_PRIME |  | 2009-009T05:36:00 |  | 000T00:40:00 | 2009-009T06:16:00 | XBAND to Earth | NEG_Y to 81.45/17.74 | SP Turn to Earth
SP_099EA_G70METSEQ009_PRIME | C | 2009-009T06:16:00 |  | 000T09:00:00 | 2009-009T15:16:00 | XBAND to Earth | NEG_Y to 81.45/17.74 | MIMI NEG_Y to Saturn (0,0, -9.5)
Apoapse Per = 9.6 d, inc =... |  | 2009-009T13:52:44 |  | 000T00:00:01 | 2009-009T13:52:45